## Submitted Apps
City of Ukiah
Submitted Planning Applications
2025-05-01
Permit # | Site Address | Date Submitted | Summary of Project | Status
17-3069 | 1294 N. State St. | 2023-07-11 | Resubmitted Major Use Permit and Site Development Permit to allow for construction of two retail suites (including one drive-through), within the Community Commercial (C1) zoning district at the "Old Tackroom" location. Original submittal 9/13/17 (File no. 17-3069). Initial DRB evaluation on January 25, 2018. | Design Review Board Hearing (DRB): 04/25/24 Recommended Approval to Planning Commission (PC); On 03/04/25 revised application and plan materials were submitted to the attention of staff; awaiting applicant response; PC Hearing: TBD
PA24-000020/21 | 534 E. Perkins St. | 2024-12-23 | Major Site Development Permit of APN 002-200-43 within the Pear Tree Center, approximately 150 feet west of the E. Perkins St./S. Orchard Ave. intersection. The proposal includes the construction of a ±1,700 sq. ft. Starbucks retail, operating as carry-out and drive-through only, with no interior dining, and a total gross building area, including the outdoor canopy, of approximately 2,885 sq. ft. The site is currently an underutilized parking lot originally developed to support the shopping center and includes access, drainage, and public utility easements. Originally, the project requested a subdivision of the existing parcel into two lots, one for future development under separate permitting processes. | Received revised project scope request to eliminate the subdivision consideration 01/23/25; awaiting updated application information; DRB & PC Hearings: TBD
PA25-000009 | 1317 Clay St. | 2025-04-01 | Minor Variance to allow a 2’ encroachment into the 5’ rear/side (southern) setback on this corner lot, for an approximately 9ft x 29ft pool and spa accessory structure. | Zoning Administrator (ZA) Hearing scheduled for 05/20/25.

## General Plan Implementation
City of Ukiah
2040 General Plan Implementation - Status
2025-05-01
General Plan Element | Implementation Program | Date Due | Description | Status / Comments
Land Use | E - Zoning Code Amendments | 2025-12-31 | Zoning districts and map consistency with the 2040 Land Use diagram. This Ordinance Amendment will facilitate the creation of an Open Space (O-S) zoning designation, as envisioned in the Ukiah 2040 General Plan. The designation seeks to preserve and manage areas of significant natural value, such as wildlife habitats, riparian corridors, creeks, and scenic resources, while supporting community resilience and sustainable land use practices. | On January 8, 2025, a Planning Commission (PC) discussion and workshop was held, presented by and in consultation with Community Development and Community Services Staff. During this session, the Commission tasked Staff with developing preliminary concepts for the Open Space Zoning District. These concepts are scheduled to be presented at the regular PC Hearing on 05/14/25.
Land Use | E - Zoning Code Amendments | 2025-12-31 | Zoning amendment to establish a consistent program for new signage, streamlining the application process and implementing design standards. This Ordinance Amendment addresses goals related to lighting, community character, and consistency across zoning designations, focusing on reducing poor signage that detracts from the built environment | On February 27, 2025, a Design Review Board (DRB) discussion and workshop was held to review and provide a recommendation to the Planning Commission on proposed ordinance amdnements regarding signage. These concepts were presented at the regular PC Hearing on April 23, 2025. The PC approved a resolution recommending the ordinance to City Council, and a resolution recommending removal of of UCC Section 3227(12). The City Council Introduction and Public Hearing are scheduled for 05/21/25.
Land Use | E - Zoning Code Amendments | 2025-12-31 | The City shall amend the Zoning Code to addres the following topics: Downtown Zoning Code and Design Guidelines | In summer 2025, the Zoning Reform Ad Hoc will meet with Staff to further potential amendments to the Downtown Zoning Code by balancing the differing needs of Perkins Street -"Revitalization" and Downtown "Preservation" as it pertains to land use and economic development.
Environment & Sustainability | H - Cultural and Historic Registry | 2025-12-31 | The City shall update the list of cultural and historic resources worthy of nomination to state or national preservation lists. | A City Council Historic Preservation Ad Hoc has been appointed by the City Council to guide this work in 2025 and 2026.
Environment & Sustainability | I - Historic Preservation Ordinance | 2030-12-31 | The City shall adopt a Historic Archaeological Preservation Ordinance to review permanent changes to the exterior or setting of designated historic or impacts to Archaeological resources. Among other topics, the Ordinance should address the following: archaeological resource impact avoidance, new development in historicallysensitive neighborhood, compatibility of energy conservation retrofitting, design review standards for new structures replacing demolished historic structures, and requirements for preservation of records and artifacts from demolished historic structures. | A City Council Historic Preservation Ad Hoc has been appointed by the City Council to guide this work in 2025 and 2026.
Environment & Sustainability | M - Adopt a Municipal Climate Action Plan (CAP) | 2025-12-31 | A Climate Action Plan (CAP) and a Climate Adaptation & Resilience Strategy (CARS) are currently being prepared. Together, the CAP and CARS will establish a strategic roadmap for how the City will reduce greenhouse gas emissions, prepare for climate hazards, & build a more resilient community. | The draft CAP will be presented to the City Council for a Public Hearing and Adoption on 05/21/25.
Economic Development | A - Economic Development Strategy | 2025-12-31 | The City shall prepare, adopt, and regularly update an Economic Development Strategy, which shall be used as an operational guide to implement the economic development goals and policies of the General Plan. | On June 19, 2024, the Ukiah City Council provided direction to Staff in the preparation of an Economic Development Strategy that guides and supports annexation efforts - an "operational guide" and to help intentionally chart a course towards the Ukiah of the future. Between August 1 and October 31, 2024, interviews were conducted with key stakeholders and community champions as identified in the Ukiah 2040 General Plan. Staff is currently analyzing the interviews to identify roughly three primary goal areas for further exploration.
Agriculture | C - Align Agricultural Standards | 2030-12-31 | Ordinance Amendment to bring consistency to Agricultural regulations of UCC with Mendocino County regulations and Ukiah 2040 Agriculture Element by amending Agricultural Combining "A" and Agriculture Exclusive "AE" zoning districts. | City Council approved introduction of the ordinance on 02/19/25; adopted by the City Council on 03/05/25.
Public Facilities, Services, and Infrastructure | B - Parks Gap Analysis | 2025-12-31 | Preparation of a parks gap analysis identifying areas of the City underserved by parks and recreation facilities access. | The Parks Gap Analysis was approved by the City Council on 03/19/2025.

## Recent Approved Projects
City of Ukiah
Recently (Within Previous 90 Days) Approved Projects
2025-05-01
Permit # | Site Address | Approved Date | Summary of Project | Comments
PA25-000007 | 105 Pomeroy Ave. | 2025-03-10 | Minor Site Development Permit for 105 Pomeroy Street (APN 002-247-02) to renovate and repurpose an existing commercial building. The project will maintain the current size and layout of the building, and will utilize the previously approved 75' pole sign. The project includes the addition of a drive-through component, and increased site landscaping. The structure, originally constructed in 1969, has historically operated as a Denny's, and has remained vacant since 2023. | Design Review Board (DRB) Hearing: 03/27/25 Recommended Approval to the Zoning Administrator (ZA); ZA approved on 04/15/25.
PA25-000005 | 195 Seminary Ave. | 2025-03-03 | Major Use Permit Renewal for 195 Seminary Avenue (APN 002-272-16) to allow for the sale and delivery of 'Cannabis Products' at an existing 'Cannabis-Related Business' within an existing commercial structure. The original 'Dispensary Use Permit' was approved by the Planning Commission on February 23, 2022. | Zoning Administrator (ZA) Hearing approved on 4/15/25.